## Sheet1
PROJECT MANAGEMENT PLANNING TOOL
|  |  | Q1 2025 | [12 empty] | Q2 2025 | [12 empty] | Q3 2025 | [12 empty] | Q4 2025
PHASE 1 | PREPARATION | Month(s) | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | NOTES
|  | Week(s) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1. | Select Topics & Define Scope
• Identify care pathway topics
• Obtain commitment from ERN Networks Lead(s)
• Appoint pathway Clinical Lead(s)
• Appoint Pathway Project Manager
• Approve care pathway topics list
• Define ‘outline pathway scope’ - condition, population(s), duration, care setting
• Briefing call with Lead / PM (if required)
• Training session for project managers / Webinar / video
• please add
Output | - List of Care Pathway Topics & Outline Pathway Scope(s)
2. | Identification of Experts & Key Stakeholders
• Map clinical disciplines required based on outline pathway scope e.g. paediatricians, geneticists, psychologists, allied health professionals
• Identify and invite expert leads from each relevant clinical discipline and expert patient leads to join a pathway development group (PDG)
• Identify wider stakeholders who can be engaged with during pathway development process incl. policy makers, hospital managers and patient groups
• please add
• xxx
Output | - List of Experts & Key Stakeholders
3. | Governance & Planning
• Prepare work plan to co-ordinate activities to develop care pathways for Phase 2 & 3
• Set up the governance structure for Pathway Development Group (PDG) & Core Writing Group (CWG)
• please add
• xxx
Output | - Governance Structure & Project Plan
PHASE 2 | SCOPE | Month(s) | January 1: January; February 6: February; March 10: March; April 14: April; May 18: May; June 23: June; July 27: July; August 32: August; September 36: September; October 40: October; November 45: November; December 49: December
|  | Week(s) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
4. | Define Pathway Parameters
• Develop a detailed pathway scope inc defining the key parameters - select patient population/procedure, stage of disease/duration of pathway, entry/exit points, care sites/settings
• Agree key outcome measures for evaluation process
• please add
Output | - Detailed Pathway Scope including parameters
5. | Gather & Appraise Guidelines & Evidence
• Gather existing guidelines and pathways & identify evidence relevant to the agreed scope
• Use existing guidelines already endorsed by ERNs and / or appraise new existing guidelines identified using international best practice, using AGREE II, (and a systematic review of the published evidence using GRADE if no approved guideline)
• please add
• xxx
Output | - Repository of Evidence & Existing Guidelines & Pathways
6. | Mapping of Current Clinical Practices
• Gather knowledge and experience from existing clinical practice / care pathways from ERN HCP members, including access to treatments via survey, workshop and / or interviews
• please add
• xxx
Output | - Baseline Pathway of Existing Care & Clinical Practice
7. | Collect Patient Needs & Experiences
• Collect patient experiences, needs, preferences, and bottlenecks and potential solutions
• Present in a patient journey
• please add
• xxx
Output | - Patient Journey
8. | Triangulate Patient Needs, Baseline Pathway & Published Evidence
• Compare baseline pathway with the patient journey to identify gaps / sticking points in the existing care pathway
• Map the published evidence, guidelines & recommendations to the baseline pathway
• Consult key stakeholders on the results from the comparison of the baseline pathway & patient journey and provide feedback
• please add
• xxx
• xxx
Output | - Main Research Findings
PHASE 3 | DEVELOPMENT | Month(s) | January 1: January; February 6: February; March 10: March; April 14: April; May 18: May; June 23: June; July 27: July; August 32: August; September 36: September; October 40: October; November 45: November; December 49: December
|  | Week(s) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
9. | Design Ideal Care Pathway
• Draft an ‘ideal care pathway’ based on the main findings of the triangulation of patient needs, baseline pathways and published evidence
• Identify supporting material
• please add
• xxx
Output | - Ideal Care Pathway & Draft Supporting Material
10. | Consensus on Evidence Gaps
• Form a consensus on any gaps in the evidence base
• please add
• xxx
Output | - Consensus Statement
11. | Revise Care Pathway & Supporting Material
• Update the ideal care pathway, and supporting material, based on the outcome of the consensus building process
• Review the format the care pathway - and decide if a graphical version of the care pathway should be developed
• please add
• xxx
Output | - Updated Care Pathway (Near-Final Draft) & Supporting Material
12. | Approval & Publication
• Internal peer review of the Final Care Pathway
• Submit final Care Pathway for approval by the Network Board, or the relevant devolved management group e.g. Executive Committee
• Develop a publication presenting the final care pathway
• Publish approved Care Pathway on the ERN website along with a peer review publication.
• please add
• xxx
• xxx
Output | - Care Pathway (Final), Supporting Publication &Communication Plan
30